## DR Tracker
[DR Fall'14]: Development of web-based GUI for LinkLayer Matlab Simulator & Sensor Test Bed
Phase 1: | Visualization Application for LinkLayer Simulator
Phase 2: | Visualization Application for Live Sensor Test bed (TutorNet)
Front End to be developed in JSP
Back End to be developed in JAVA
Phase 1:
| Requirement Gathering/Ramp up | Status
| Get Familiar with Matlab Link layer Simulator. | Done
| Input and Output Data Formats | In Progress
| Architecture Design | In Progress
| Indoor RTH Floor Plan | Open
| Java/JSP tutorials and Interworking | In Progress
| Matlab Interface for Java Back End | In Progress
| Front End Work Tasks Breakdown | Effort(in Hrs) | Status
| Eclipse IDE, JAVA SDK, JRE | 2 | Done
| Apache Server Setup | 6 | In Progress
Front End Web Page Layout Mock Up
| Basic 2D MAP integration with JSP | 5 | In Progress
| Matlab GUI mimick in Web Interface | 3 | In Progress
| Web Layout View Implementation | 10 | Open
| Java Servlets | 4 | TBD
| Integration of RTH indoor Map & Integration of Google APIs | TBD | TBD
| Java Script to check java installed on client | TBD | TBD
| Back End Work Tasks Breakdown | Effort(in Hrs) | Status
| UML Design | 4 | In Progress
Java Method Creation
| Handler for Input.m creation | 3 | In Progress
| Handler for Topology.m creation | 3 | In Progress
| Handler for LinkLayerModel.m execution | TBD | TBD
| Exception Handling | TBD | TBD
| Logging Framework | TBD | TBD

## Weekly-Milestone
Week Ending | Top Level Milestone | Delivery Status
2014-12-21 | Report
2014-12-14 | Buffer time ( Enhanchements and Bud fixes)
2014-12-07 | Deployment and Testing.
2014-11-30 | Phase 2 - Programming
2014-11-23 | Phase 2 - Design + Programming
2014-11-16 | Phase 2 - Requirement Gathering + Analysis
2014-11-09 | Project - Phase 1 + Server/Deployment
2014-11-02 | Project - Phase 1 + Local Setup
2014-10-26 | Project issues/updates/Architecture redesign