## DR Tracker
[DR Fall'14]: Development of web-based GUI for LinkLayer Matlab Simulator & Sensor Test Bed
Phase 1: | Visualization Application for LinkLayer Simulator
Phase 2: | Visualization Application for Live Sensor Test bed (TutorNet)
Front End to be developed in JSP
Back End to be developed in JAVA
Architecture
Front end to be developed in HTML/CSS, Java Script
Restful webservice
Backend to be developed in Java
Git Hub Repo
https://github.com/venk3389/EE590_DR_FALL2014
Phase 1:
| Requirement Gathering/Ramp up/Issues/Setups | Status
| Get Familiar with Matlab Link layer Simulator. | Done
| Input and Output Data Formats | Done
| Architecture Design | Done
| Indoor RTH Floor Plan | Done
| Java/JSP/Java servelet,script tutorials and Interworking | Done
| Matlab Interface for Java Back End | Done
| Git Hub repository creation | Done
| Octave Interface as an alternative option exploration | Done
| Data handling between Server and Client | Open
| Manual Node placement option in Web Gui | Open
| Ways to implement data visualization from Matlab | Open
| Front End Work Tasks Breakdown | Effort(in Hrs) | Status
| Eclipse IDE, JAVA SDK, JRE | 2 | Done
| Apache Server Setup | 6 | In Progress
Front End Web Page Layout Mock Up
| Basic 2D MAP integration with JSP | 5 | In Progress
| Matlab GUI mimick in Web Interface | 3 | In Progress
| Adding the restful webservice structure to Java servlets | 6 | Done
| Web Layout View Implementation | 30 | In Progess
| Java Servlets | 4 | Done
| Matlab Test Data set visualization | 25 | In Progress
| Integration of RTH indoor Map & Integration of Google APIs | TBD | TBD
| Java Script to check java installed on client | TBD | TBD
| Understanding Matlab Plot nodes code | 5 | In Progress
| Bootstraps to provide a graphical visualization |  | In Progress
| Back End Work Tasks Breakdown | Effort(in Hrs) | Status
| UML Design | 4 | Done
| Matlab Interface Redesign | 4 | Done
Java Method Creation
| Handler for Input.m creation | 3 | In Progress
| Handler for Topology.m creation | 3 | In Progress
| Handler for LinkLayerModel.m execution | 10 | Done
| Data Extraction from Matlab to Java | 6 | Done
| Test Data Set Generation | 1 | Done
| Concurrent Matlab Instance Handler | 8 | In Progress
| Exception Handling | 5 | In Progress
| Logging Framework | 5 | In Progress
| Input/Output Interface to Java Servlet | 15 | In Progress

## Weekly-Milestone
Week Ending | Top Level Milestone
2014-12-17 | Report
2014-12-14 | Buffer time ( Enhanchements and Bud fixes)
2014-12-07 | Deployment and Testing.
2014-11-30 | Phase 2 - Programming
2014-11-23 | Phase 2 - Design + Programming
2014-11-16 | Phase 2 - Requirement Gathering + Analysis
2014-11-09 | Project - Phase 1 + Server/Deployment
2014-11-02 | Project - Phase 1 + Local Setup
2014-10-26 | Project issues/updates/Architecture redesign
2014-10-19 | Implementation & Issues Found
2014-10-12 | Key technologies ramp up
2014-10-05 | Phase 1 Architecture
2014-09-28 | Phase 1 Project Requirement Gathering
2014-09-21 | Understanding the Matlab Simulator & Environment
2014-09-17 | Project Kickoff Discussion with Prof. Bhaskar